Table of Contents

1.	Initiating Tasks	2

1.1	Business Case	2

1.2	Three Sphere’s Model	5

1.3	Project Charter	6

2.	Planning Tasks	8

2.1	Scope Statement	8

2.2	WBS	9

2.3	Work Item List	9

2.4	Cost Estimate	10

2.5	Communication Management Plan	11

2.6	Quality Management Plan	13

2.7	Risk Management Plan	16

2.8	Stakeholder Management Plan	23

3.	Conclusion	27

References	28

# Initiating Tasks

## Business Case

Project Name: EcoPantry: Smart Inventory and Food Sharing application to Reduce Food Waste

Introduction/ Background: EcoPantry is a proposed mobile application which is designed to reduce household food waste through inventory management, expiry alerts, donation facilities and meal planning. “Malaysia generates approximately 17,000 tons of food waste daily, with household food waste forming a significant portion.” (Ashley Yeong, 2024, para 1). EcoPantry tackles this problem by providing a digital platform that tracks, donates and plans their food consumption more effectively and intuitively.

2.0 Business Objective To launch EcoPantry as a functional digital solution to contribute towards the national food waste reduction efforts. The project aims to support responsible consumption and expansion of community food donation networks.

3.0 Current Situation and Problem/Opportunity Statement Current Situation: Most households don’t rely on tracking food inventory and expiry dates which causes unnecessary waste. Which often leads to overstocking of ingredients, food expiry before use, and lack of data for management of inventory. Existing grocery, to-do list, or donations apps address only one part of the problem. This project takes advantage of the opportunity granted by these applications to create an integrated, privacy-conscious platform which combines inventory management, expiry alerts, donation facilitation, and meal planning.

4.0 Critical Assumption and Constraints Assumptions: - Target users own smartphones and are willing to share food in exchange for waste reduction benefits. - Local community and people will be willing to participate in donation making partnerships - Users have basic computer literacy. - Internet connectivity is available. Constraint: - Project must be completed within the given time frame. - Total budget will be capped as detailed in Cost Estimate. - Software must be compatible with most mobile devices currently in use.

5.0 Analysis of Options and Recommendation Option 1: Do nothing Advantage: One can continue using manual systems so no development cost. Disadvantage: High food wastage and inefficient operations. Option 2: Purchase Existing Software Advantage: No development cost and faster implementation of the software. Disadvantages: It may include expensive licensing and reduced efficiency. Option 3: Develop EcoPantry Advantage: It gives full control over the features and stronger data privacy. Disadvantage: The initial development cost should be made. Recommendation: The recommended option is the third option to develop EcoPantry because it provides best features with best long-term value. Although the initial development cost will be high it will improve efficiency and ROI also indicates a positive return on investment.

6.0 Preliminary Project Requirements - It should have intuitive application user interface - It should have secure and private user registration and login - It should have food inventory and food logging system - It should have real-time notification system to alert the users. - It should have weekly food tracker to register weekly food consumption

7.0 Budget Estimate and Financial Analysis The total project cost is estimated at $18,480. A 3-year financial analysis was performed at a discount rate of 8%, covering Year 0 (development) and Years 1-3 (operations). Ongoing annual costs (hosting, maintenance, and support) are estimated at $8000 in year 1, which grow 10% per year. The analysis yields an NPV of $105,984, an ROI of 257.8% and a pay back period early in Year 1. Summary of calculations and assumptions are provided in Exhibit A.

8.0 Schedule Estimate The estimated project timeframe is 14 weeks from 18 May 2026 to 24 August 2026. Which includes Initiating, Planning, Executing (requirements, design, development, integrations and testing) and Closing (deployment, final report and presentation), with Monitoring and Controlling activities running throughout.

9.0 Potential Risks - There may be issues between front-end, back-end and APIs. - The users may be reluctant to share household food data. - The balance of work between the team members may be limited. - Issues with privacy could result in legal and reputational issues.

10.0 Exhibits Exhibit A: Financial Analysis - Total Discounted Costs: The present value of all project costs amounts to $41,116. - Total Discounted Benefits: The present value of the project benefits totals $147,100. - Net Present Value (NPV): The project yields a positive NPV of $105,984. - Payback Period: The initial investment is recovered in Year 1, as the cumulative cash flow turns positive at $6,520. - Return on Investment (ROI): The project delivers a strong ROI of 257.8%.

## Three Sphere’s Model

## Project Charter

| Project Title: EcoPantry: Smart Inventory and Food Sharing application to Reduce Food Waste |  |  |  |
| --- | --- | --- | --- |
| Project Start Date: 18 May 2026 Projected Finish Date: 24 August 2026 |  |  |  |
| Budget Information: The Total estimated project cost is $18,480 as per the Cost Estimate. This covers hours of labor by the internal team members at the rate of $20 per hour, non-labor costs such as cloud hosting, API services, deployment ($2000) and a 10% contingency reserve. The team is self-funded, and the budget represents the opportunity cost of team members. |  |  |  |
| Project Manager: Mijala Shristi Bajracharya, 9866290717, mijala.shristi.bajracharya23@midvalley.edu.np |  |  |  |
| Project Objectives: - To design and develop a fully functional mobile application within 14 weeks and within the approved budget. - To deliver all six-core use cases that meet the requirements defined in the scope statement. - To ensure data privacy and security - To provide real-time notification system to alert the users |  |  |  |
| Success Criteria: - All six use cases are implemented and are functional - Project completed within the timeframe and budget - Positive User testing experience - All project deliverables submitted on time and approved by the course lecturer. |  |  |  |
| Approach: This project team will follow the PMBOK based project management framework entailing Initiating, Planning, Executing, Monitoring and Controlling, and Closing. It will combine this framework with an iterative, sprint-based software development approach for execution. Weekly meetings will be conducted to ensure smooth progress and tools like GitHub will be used for collaboration, version control and documentation. |  |  |  |
| Roles and Responsibilities |  |  |  |
| Name and Signature | Role | Position | Contact Information |
| Mijala Shristi Bajracharya | Project Manager | Team Lead | mijala.shristi.bajracharya@midvalley.edu.np |
| Sailabee Shrestha | Developer | Team Member | sailabee.shrestha23@midvalley.edu.np |
| Anjana Thapa | Developer | Team Member | anjana.thapa23@midvalley.edu.np |
| Seetha Letchumi | Project Sponsor | Course Lecturer |  |
| Comments: |  |  |  |

# Planning Tasks

## Scope Statement

Project Title: EcoPantry Smart Inventory and Food Sharing application to Reduce Food Waste Date: 18 May 2026 Prepared by: EcoPantry Team

Project Justification: To combat the significant food waste generated by Malaysian households and to take advantage of the gap generated by existing application EcoPantry combines inventory tracking, expiry alerts and community donation in one place. EcoPantry sole purpose is to reduce food waste.

Product Characteristics and Requirements: - User registration and Privacy settings should include 2FA. - Inventory management should include add/edit/delete items, expiry date, category and storage of locations. - Convert inventory items to donation listings - Notification system for expiry alerts, donation updates. - Weekly meal planning based on available inventory.

Product User Acceptance Criteria: The product will be accepted when: all six use cases function properly, registration and login have 2FA validation, donation listing can be posted, browsed, and claimed, notifications are triggered, passing UAT, the application is successfully deployed. Summary of Project Deliverables Project management-related deliverables: business case, project charter, team contract, scope statement, WBS, work items list, project schedule, cost estimate, communications/quality/risk management plans, stakeholder management strategy, status reports, final project presentation, final project report, and lessons-learned report. Product-related deliverables: requirements documentation, use-case models and UI/UX designs, database design, source code for the web/mobile application, test plans and reports, deployed application, and a user manual.

## WBS

## Work Item List

## Cost Estimate

| WBS Category | Hours | Labor Cost ($) | Non-Labor Cost ($) | Total Cost ($) |
| --- | --- | --- | --- | --- |
| 1. Initiating | 40 | 800 | 0 | 800 |
| 2. Planning | 90 | 1,800 | 0 | 1,800 |
| 3. Executing (Requirements, Design, Development, Integration, Testing, Deployment) | 500 | 10,000 | 1,800 | 11,800 |
| 4. Monitoring & Controlling | 70 | 1,400 | 0 | 1,400 |
| 5. Closing | 40 | 800 | 200 | 1,000 |
| Subtotal | 740 | 14,800 | 2,000 | 16,800 |
| Contingency Reserve (10%) | — | — | — | 1,680 |
| Total Project Cost | 740 | — | — | 18,480 |

Here is a summary of cost estimate from the excel sheet of cost estimate:

- Total Labor Effort: 740 hours (Internal labor rate is $20/hour).

- Total Base Costs: $16,800(which consists of $14,800 in Internal Labor and $2,000 in Non-Labor costs).

- Contingency Reserve: A 10% reserve ($1,680) has been added to the base cost.

- Total Project Budget: The final approved budget, including contingency, is $18,480 (matching the Year 0 cost in the financial analysis).

Note: This cost estimate considers the most optimistic approach for this project to ensure that the project feels more viable.

## Communication Management Plan

| No | Stakeholder | Position | Role | Communications plans |
| --- | --- | --- | --- | --- |
| 1 | Mijala Shristi | Project lead | The leadership of the project in the artistic aspect. | Weekly team stand-up (Google Meet, every Friday- Saturday 7 PM). Responds to lecturer with status email on a weekly basis – every Friday. Sustains common project board on Trello. |
| 2 | Anjana | Developer / Backend Lead | System Developer | Daily async updates given through WhatsApp group. Pushes code to common GitHub repository every day. Attends weekly stand-up. Provides feedback to design documents through Google Docs, using comments in-line. |
| 3 | Sailabee | Designer / Frontend Developer | UI/UX & frontend dev | Provides wireframes through Figma to get feedback asynchronously. Participates in weekly stand-up. Posts design decisions on shared Google Doc for transparency. |
| 5 | Participants in the UAT | participants who are test users | provide usability feedback | recruited using email/WhatsApp in Week 13. Feedback collected through Google Forms testing. Feedback provided with team within 24 hours of every session. |

## Quality Management Plan

| No | Project Characteristic/Requirement | Quality standard | Metric |
| --- | --- | --- | --- |
| 1 | User Registration & 2FA (UC1) | All new users should be able to register and receive a verification email and activate account with 2FA should take less than 5 minutes. | All 90% of test cases must pass. A verification email is sent within 60 seconds. Measured using an automatic test suite. |
| 2 | Food Inventory Management (UC2) | User should be able to add, edit, delete, and change a food item into a donation listing without errors. The inventory must be updated as soon as changes occur. | No critical bugs found on Inventory CRUD operations in UAT. The website loads after adding/editing something < 1 second. |
| 3 | Donation Browse & Claim (UC3) | Users should be able to browse and filter listings of donations and be notified within 10 seconds of claiming an item. | Fast response time of filter (less than 2 seconds). Donor gets confirmation of the claim in 10 seconds. Evaluated on 5 sessions of use. |
| 4 | Food Analytics Dashboard (UC4) | The Analytics Dashboard should accurately represent total items saved, donated, and planned. Charts should be updated as data changes. | Data accuracy: 90% match between the data displayed and the data in the database. Chart rendering time < 3 seconds for up to 1,000 records. |
| 5 | Notification Delivery (UC5) | Expiry alerts need to be delivered no less than 3 days prior to the expiry date. All notifications should be received in the user's notification inbox within 1 minute. | A 90% of notifications in 60 seconds. No expiry notifications missed in test scenarios. Tested using QA test scripts. |
| 6 | Meal Planning (UC6) | Users should be able to enter and connect all 7 daily meals for the week and be able to do this without making errors. The inventories should be adjusted after confirmation of meals. | All plans for the 7-day period are saved. Reserved quantity for inventory is updated in real time after plan is confirmed (2 seconds). Tested in integration tests. |
| 7 | System Performance | The application should be able to support up to 1000 users concurrently and load time of all core screens should be less than 2 seconds. | 1000 simulated users, response time 95th percentile is less than 2 seconds. Performed through Apache JMeter and/or Locust. |
| 8 | Security & PDPA Compliance | All personal user data is to be encrypted during transfer (HTTPS) and in storage. The app should be compliant with the Malaysian Personal Data Protection Act (PDPA) 2010. | The SSL Certificate is active and has been checked using a browser' audit of security. Preparing the PDPA Compliance checklist and signing it off prior to the launch. Security audit is done by Week 13. |
| 9 | Code Quality | All code modules should have at least 70% automated test coverage. There must be a second team member to review the code before it is merged too main. | Weekly code coverage report generated with Jest/Flutter test. All PRs are reviewed and approved prior to merge. No critical SonarQube issues in final release. |
| 10 | User Satisfaction | At least 80% of UAT participants need to rate the usability and usefulness of the app as satisfactory or above (4/5 stars). | Google Form feedback from students after every session at UAT. Average score calculated. Minimum: 4.0/5.0 in overall satisfaction. |

## Risk Management Plan

1. Methodology

The EcoPantry project is a student software project that has a fixed 14-week schedule, so it requires a light-weight approach to risk management that's suitable for that environment. It is a process with four recurring activities:

- Risk Identification – risks are discussed at weekly stand-ups, sprint planning and UAT sessions, and logged in the shared risk register (Trello + this document).

- Qualitative Risk Analysis – each risk is allocated a Probability × Impact rating (Low / Medium / High / Very High) which defines the priority of each risk (see Section 5).

Risk Response Planning – involves decision making about a response to each risk (Avoid, Mitigate, Transfer, except for negative risks (threats) and Exploit, Enhance, Share, and Accept for positive risks (opportunities)).

Risk Monitoring and Control – The risk register is updated on Fridays during the team stand-up, new risks are added, and the status of risks is reviewed until the project is closed in Week 14.

Sources of data for the identification process include team retrospectives, Work Breakdown Structure, Requirements Specification and Design Document, and direct feedback from the UAT participants.

2. Roles and Responsibilities

The three-member EcoPantry team share ownership of the risks, meaning that there are no unmonitored risk categories. Responsibilities are summarized below.

| Role | Team Member | Risk Management Responsibilities |
| --- | --- | --- |
| Project Manager / Risk Owner (overall) | Mijala | Owns the risk register, leads weekly risk review, escalates critical/extreme risk to the lecturer, approves response strategies. |
| Technical Risk Owner | Anjana | Keeps an eye on the technical risks like API failure, budget of dev effort etc. and reports at stand-ups. |
| Design / UX Risk Owner | Sailabee | Tracks changes and usage; tracked usability and UAT-related risks; provides UAT feedback for risk updates. |
| All team member | Whole Team | as new risks emerge, identify them in the shared Trello board and add agreed mitigation steps in their tasks. |

At the set time of milestone reviews (Weeks 4, 8 and 12), the Project Manager will bring together all risk updates and report to the module lecturer on any new critical risks, realised risks or closed risks.

3. Budget and Schedule

A contingency reserve of $1680 (around 10% of the estimated project budget) has been allocated for realized risks including any budget overrun or for paid third party tooling. This reserve is audited weekly in conjunction with actual expenditure.

There is no extra risk meeting time and risk management activities are integrated into the current 14-week project schedule at no extra cost in time: risk reviews are held at the Friday stand-up (30 minutes), and risk identification is done as part of this review. Targeting feature complete status by Week 11 and allowing for schedule buffer in Weeks 12-14 for risk response and UAT-driven rework ensures time contingency is built in.

4. Risk Categories

Risks are categorized in a project specific Risk Breakdown Structure (RBS) that includes the following categories:

- Structure / Process – scope and change management, compliance (scope creep, PDPA non-compliance).

- People – team capacity and availability (e.g. team member drop out).

- Technology – risks of development tools, APIs, and technology integrations (such as faster development, or failure of technology integration).

- Financial – risks relating to project budget and cost estimation (e.g. budget overrun).

- Market – risks associated with end users and external partners (e.g. low uptake by users, interest of the NGO/partners).

5. Risk Probability and Impact

Every risk is assessed on a 5-point scale when it comes to the likelihood of it occurring, and its impact on project objectives (scope, schedule, cost, quality). The overall risk severity is a combination of the two; see the matrix below.

|  | Very Low | Low | Medium | High | Very High |
| --- | --- | --- | --- | --- | --- |
| Very High Impact | Low | Medium | High | Extreme | Extreme |
| High Impact | Low | Medium |  | Extreme | Extreme |
| Medium Impact | Low | Low | Medium | High | High |
| Low Impact | Low | Low | Low | Medium | Medium |

High and Extreme risks (such as Scope Creep, PDPA Non-Compliance) are reviewed weekly, but not just any time, and must be responded to through documentation prior to the next stand-up. Risks rated Medium are reviewed at each milestone. Low risk events: events are monitored passively and reassessed when conditions change.

Below is the Risk Register Table:

| Rank | Risk Name | Description | Category | Response strategy | Probability | Impact | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Scope Creep | When new features are added to a project during its development and cause the project to miss deadlines and exceed its budget. | Structure / Process | Mitigate: Establish formal change control; record all change requests; raise with lecturer. | High | High | Critical – must be monitored weekly. |
| 2 | Team Member Dropout | A team member leaves the course or is unavailable, which decreases team capacity. | People Risk | Mitigate: Cross train members, Document all work. Accept: Share tasks with other members, if feasible. | Medium | High | Early detection via weekly check-ins. |
| 3 | Tech Integration Failure | Third party APIs (notification service, map APIs) cease to be available or are updated without warning. | Technology | Mitigate: Use abstraction layers, have fallback providers identified. Contingency: Create in-app notification inbox as an offline alternative. | Medium | Medium | Review API T&Cs before integration. |
| 4 | Budget Overrun | The complexity has been underestimated or there are extra tooling requirements that have caused the actual costs to surpass budgeted amount. | Financial | Mitigate: Monitor weekly expenditure against budget; use open-source tools. Transfer: If necessary, use contingency reserve (RM 1,896). | Low | High | Weekly budget review by PM. |
| 5 | Low User Adoption | Target users do not download EcoPantry or regularly use it, which hinders the social impact of the project. | Market | Mitigate: Provide onboarding tutorial; collect feedback throughout UAT and refine. Accept: Ignore any use cases that do not appear to be engaged enough to focus on. | Medium | Medium | Monitor UAT satisfaction scores. |
| 6 | PDPA Non-Compliance | If they are not compliant with the Malaysian Personal Data Protection Act (PDPA) 2010 and put the project at risk of legal action. | Structure / Process | Avoid PDPA compliance review until week 10. Add privacy policy and data consent forms to the app. | Low | Very High | Legal issue; zero tolerance. |
| 7 | NGO / Partner Interest | Local NGOs/Food Banks show interest in becoming partner with EcoPantry and open opportunities for more funding and more numbers of users. | Market | Exploit: Make a partnership proposal and demo ready by Week 12 and capitalize on this opportunity. | Medium | Heigh | Positive risk – actively pursue. |
| 8 | Faster Development | The team finishes development modules sooner than planned because of reusability and/or higher productivity. | Technology | Exploit: Take some extra time to add stretch capabilities (such as multi-language UI), or to add more tests. | Medium | Medium | Positive risk – plan buffer tasks. |

## Stakeholder Management Plan

A stakeholder management strategy was created for each team member from the analysis of the stakeholders' influence and interest.

Stakeholder Power/Interest Matrix:

| Stakeholder Strategy | Interest | Influence | Quadrant | Management Strategy |
| --- | --- | --- | --- | --- |
| Seetha Letchumi (Lecturer) | High | High | Manage Closely | Mijala Strategy: Give structured summaries of milestones at the end of Weeks 4, 8 and 12. Ask a signature at each stage. Please reply to all feedback within 48 hours. Conduct face-to-face consultation at the 7th point of the project review. |
| Team Members (3) | High | High | Manage Closely | Anjana Strategy: Conduct weekly Monday stand-ups (30 mins). Keep a shared Trello board and have the status of tasks updated in real time. Respond to address blockers within 24 hours. Reward milestone achievements to keep morale and engagement high. |
| UAT Participants (5+ users) | Medium | Low | Keep Informed | Sailabee Strategy: Recruit participants by Week 12 through personal network. Give explicit UAT instructions and a Google Form feedback form. Provide an overview of the modification(s) implemented based on their feedback. Recognize their involvement in the final report. |
| Potential NGO Partners | Low | Medium | Keep Informed | Mijala: Invite to Week 14 demo session if interest is expressed. Keep professional communications and take on any questions regarding the donation abilities of the platform promptly. |
| End Users (Households) | High | Low | Keep Informed | Anjana Strategy: Ensure intuitive onboarding; design the app with empathy for End Users (Households). Gather feedback throughout UAT. Communicate via in-app notifications. Create a quick FAQ and User Guide for the app help page. |

The members of each team will be responsible to oversee stakeholders in their assigned quadrant. The Project Manager is responsible for keeping stakeholders happy and transferring un-resolved stakeholder issues to the lecturer as appropriate.

# Conclusion

The EcoPantry project offers an innovative solution to address the growing problem of household food waste in Malaysia through features like food inventory management, expiry alerts, meal planning and donation. This project management plan has all the things like scope, objectives, budget, timeline, quality standards, communication strategies, risk management, and stakeholder responsibilities that establish a clear roadmap for the development of the application. The financial analysis also indicates that the project is feasible, with a positive NPV, strong ROI and an acceptable payback period.

GitHub Link

https://github.com/Mijala-SB/EcoPantry

# References

- Personal Data Protection Act 2010 (Act 709) (Malaysia).

- Project Management Institute. (2021). A guide to the project management body of knowledge (PMBOK® guide) (7th ed.). Project Management Institute.

- Schwalbe, K. (2015). Information technology project management (8th ed.). Cengage Learning.

- United Nations. (n.d.). Goal 12: Ensure sustainable consumption and production patterns. Sustainable Development Goals. https://sdgs.un.org/goals/goal12

- Yeong, A. (2024). How Malaysians are battling food waste with surplus food. FairPlanet. https://www.fairplanet.org/editors-pick/how-malaysians-are-battling-food-waste-with-surplus-food/

- Claude & Bajracharya, M.S(2026, July 10). Help me with the data for the financial analysis and cost estimate for assignment 1 [AI-generated text]. Anthropic. https://claude.ai/chat/165cafe4-0e3e-4cb4-aec5-907ba7e6b9cd