## Sheet1
EcoPantry
Task No | Task Name |  |  | Duration(days) | Precedence | Mijala Shristi Bajracharya | Sailabee Shrestha | Anjana Thapa
1 | Planning
| 1.1 | Brainstroming |  | 1 |  | 100 | 100 | 100
| 1.2 | Feasibility Study
|  | 1.2.1 | Requirement Analysis | 1 | 1.1 | 100 | 100 | 100
|  | 1.2.2 | Target User Research | 1 | 1.1 | 100 | 100 | 100
|  | 1.2.3 | Food Waste Problem Analysis | 1 | 1.1 | 100 | 100 | 100
2 | Design
| 2.1 | Structure Diagram
|  | 2.1.1 | Class Diagram | 3 | 1.2.1 | 100
|  | 2.1.2 | Flow Chart | 2 | 1.2.2 |  | 100
|  | 2.1.3 | ER Diagram | 2 | 1.2.3 |  |  | 100
| 2.2 | UI/UX Design
|  | 2.2.1 | Wireframes | 3 | 2.1.1 | 50 |  | 50
|  | 2.2.2 | Prototype(mobile screens) | 4 | 2.2.1 |  | 100
3 | Development
| 3.1 | User Registration and login module
|  | 3.1.1 | Secure Sign-UP | 3 | 2.2.2 | 100
|  | 3.1.2 | Login Authentication | 2 | 3.1.1 | 100
| 3.2 | Food Inventory Module
|  | 3.2.1 | Add/Edit Food Items | 3 | 3.1.2 |  | 100
|  | 3.2.2 | Food Logging system | 3 | 3.2.1 |  | 100
|  | 3.2.3 | manual expiry date input | 2 | 3.2.1 |  |  | 100
| 3.3 | Notification Module
|  | 3.3.1 | Real-Tiime Expirey Alert | 3 | 3.2.2 |  |  | 100
|  | 3.3.2 | Weekly food Tracker | 3 | 3.2.2 | 100
| 3.4 | Food Sharing module
|  | 3.4.1 | Donate Food Feature | 3 | 3.3.1 |  | 100
|  | 3.4.2 | Pick-Up Food Feature | 3 | 3.4.1 |  |  | 100
4 | Testing
| 4.1 | Unit Testing |  | 2 | 3.4.2 | 50 | 50
| 4.2 | Integration Testing |  | 2 | 4.1 | 50 |  | 50
| 4.3 | UI/UX Testing |  | 2 | 4.1 |  | 50 | 50
| 4.4 | User Acceptance Testing |  | 3 | 4.2 |  | 50 | 50
5 | Deployment
| 5.1 | App store Submission |  | 2 | 4.4 | 50 | 50
| 5.2 | User Documentation |  | 2 | 4.4 |  |  | 100
| 5.3 | Project Report finalisation |  | 3 | 5.1 | 34 | 33 | 33