## Financial Analysis
Financial Analysis for EcoPantry: Smart Inventory and Food Sharing application to Reduce Food Waste
Created by:EcoPantry Team |  | Date: | 2026-05-18
Discount rate | 8%
Assume the project is completed in Year 0
Year
| 0 | 1 | 2 | 3 | Total
Costs ($) | 18480 | 8000 | 8800 | 9680
Discount factor | 1 | 0.92593 | 0.85734 | 0.79383
Discounted costs | 18480 | 7407.4074 | 7544.5816 | 7684.2961 | 41116.2851
Benefits ($) | 0 | 35000 | 56000 | 84000
Discount factor | 1 | 0.92593 | 0.85734 | 0.79383
Discounted benefits | 0 | 32407.4074 | 48010.9739 | 66681.9082 | 147100.2896
Discounted benefits - costs | -18480 | 25000 | 40466.3923 | 58997.6122 | 105984.0045 | NPV
Cumulative benefits - costs | -18480 | 6520 | 46986.3923 | 105984.0045
ROI | 257.8%
Payback in Year 1 (approx. 0.74 of the way through Year 1, i.e. ~9 months after project completion)
Assumptions
1. Year 0 development cost of $18,480 is taken directly from the project Cost Estimate (Subtotal + 10% contingency reserve).
2. Years 1-3 operating costs cover cloud hosting, database/API services, app maintenance, and customer support, estimated at $8,000 in Year 1 and growing 10% p.a. as the user base grows.
3. Benefits comprise: (a) premium subscription revenue at $5/user/month, assuming 500 premium users in Year 1, 800 in Year 2, and 1,200 in Year 3; and (b) partnership/referral fees from grocery retailers and NGOs for donation-matching ($5,000 in Year 1, $8,000 in Year 2, $12,000 in Year 3).
4. No revenue is generated in Year 0 as the app is still in development and has not launched.
5. A discount rate of 8% is applied per the assignment brief, over a 3-year post-launch period (Years 1-3), in addition to Year 0 (development).
6. All figures are in US Dollars (USD) and are estimates for planning purposes; actual results may vary with user adoption and market conditions.
Formulae used:
Discount factor (Year n) = 1 / (1 + discount rate)^n
Discounted Cost (Year n) = Raw Cost (Year n) × Discount Factor (Year n)
Discounted Benefit (Year n) = Raw Benefit (Year n) × Discount Factor (Year n)
Net (Year n) = Discounted Benefit (n) − Discounted Cost (n)
NPV = Σ (Discounted Benefits − Discounted Costs), Years 0–3 = −18,480 + 25,000 + 40,466 + 58,998 = $105,984
ROI = NPV / Total Discounted Costs = 105,984 / 41,116 = 2.578 → 257.8%
Cumulative (Year n) = Cumulative (Year n−1) + Net (Year n)
Payback = Year of crossover + (¦cumulative at start of that year¦ / net cash flow that year)
= 0 + (18,480 / 25,000) = 0.74

## Cost Estimate
Cost Estimate
Project Name: EcoPantry: Smart Inventory and Food Sharing application to Reduce Food Waste | Date: | 2026-05-18
Assumed internal labour rate ($/hour): | 20 |  | Contingency reserve (%): | 10% | [5 empty] | Weekly Cost Breakdown
| Internal Values | $/hour | Internal $Total | External Labor | $/hour | External $Total | Total Labor | Non-labor $ | Total Cost | WBS Activity | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14 | Total Hrs | Cost ($)
WBS Categories | [9 empty] | 1. Initiating (Business Case, Three-Sphere Model, Charter) | Wk1: 25; Wk2: 15 | 40 | 800
1. Initiating | 40 | 20 | 800 | 0 | 0 | 0 | 800 | 0 | 800 | 2. Planning (Scope, WBS, Work Items, Cost Estimate, Mgmt Plans) | Wk2: 15; Wk3: 45; Wk4: 30 | 90 | 1800
2. Planning | 90 | 20 | 1800 | 0 | 0 | 0 | 1800 | 0 | 1800 | 3.1 Requirements Gathering & Analysis | Wk4: 10; Wk5: 30 | 40 | 800
3. Executing | [9 empty] | 3.2 System & UI/UX Design | Wk5: 20; Wk6: 30 | 50 | 1000
3.1 Requirements Gathering & Analysis | 40 | 20 | 800 | 0 | 0 | 0 | 800 | 0 | 800 | 3.3 Database Design & Setup | Wk6: 15; Wk7: 25 | 40 | 800
3.2 System & UI/UX Design | 50 | 20 | 1000 | 0 | 0 | 0 | 1000 | 0 | 1000 | 3.4 Front-End Development | Wk6: 10; Wk7: 25; Wk8: 40; Wk9: 45 | 120 | 2400
3.3 Database Design & Setup | 40 | 20 | 800 | 0 | 0 | 0 | 800 | 0 | 800 | 3.5 Back-End Development & API Integration | Wk6: 15; Wk7: 30; Wk8: 45; Wk9: 40 | 130 | 2600
3.4 Front-End Development | 120 | 20 | 2400 | 0 | 0 | 0 | 2400 | 400 | 2800 | 3.6 System Integration | Wk9: 15; Wk10: 25 | 40 | 800
3.5 Back-End Development & API Integration | 130 | 20 | 2600 | 0 | 0 | 0 | 2600 | 0 | 2600 | 3.7 Testing & Quality Assurance | Wk10: 25; Wk11: 35 | 60 | 1200
3.6 System Integration | 40 | 20 | 800 | 0 | 0 | 0 | 800 | 800 | 1600 | 3.8 Deployment & Launch Preparation | Wk12: 20 | 20 | 400
3.7 Testing & Quality Assurance | 60 | 20 | 1200 | 0 | 0 | 0 | 1200 | 0 | 1200 | 4. Monitoring & Controlling (PM tracking, status reports) | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 70 | 1400
3.8 Deployment & Launch Preparation | 20 | 20 | 400 | 0 | 0 | 0 | 400 | 600 | 1000 | 5. Closing (Final Report, Presentation, Lessons Learned) | Wk13: 20; Wk14: 20 | 40 | 800
4. Monitoring and Controlling | 70 | 20 | 1400 | 0 | 0 | 0 | 1400 | 0 | 1400 | Total Hours / Week | 30 | 35 | 50 | 45 | 55 | 75 | 85 | 90 | 105 | 55 | 40 | 25 | 25 | 25 | 740 | 14800
5. Closing | 40 | 20 | 800 | 0 | 0 | 0 | 800 | 200 | 1000 | Cost / Week ($) | 600 | 700 | 1000 | 900 | 1100 | 1500 | 1700 | 1800 | 2100 | 1100 | 800 | 500 | 500 | 500
Subtotal | 740 |  | 14800 | 0 |  | 0 | 14800 | 2000 | 16800
Reserves (contingency) | [8 empty] | 1680
Total | 740 |  | 14800 | 0 |  | 0 | 14800 | 2000 | 18480
Assumptions
1. Team of 3 members (Project Manager, Full-Stack Developer, UI/UX Designer & QA Tester) working part-time (approx. 10-15 hrs/week each) over 14 weeks.
2. A single blended internal labour rate of $20/hour is used across all team members and WBS categories (average of PM/Developer/Designer market rates for student/junior IT professionals).
3. No external/outsourced labour is used; all work is completed in-house by the project team.
4. Non-labour costs cover: front-end tooling & design software licences ($400), cloud hosting/database/API services ($800), app store, domain & deployment costs ($600), and printing/presentation costs for closing ($200).
5. A 10% contingency reserve is applied to the subtotal to account for scope changes, rework, and estimation uncertainty.
6. Total cost estimate feeds directly into the Business Case Financial Analysis (Year 0 development cost) and the Project Charter budget.

## Payback
Payback Period Chart for EcoPantry
Created by: EcoPantry Team |  |  | Date: | 2026-05-18
Note: Discounted costs and benefits below are taken from the Financial Analysis (Business Case).
Years 0-3 = project development year plus three post-launch years. Discount rate: 8%.
Year | Costs | Benefits | Cum Costs | Cum Benefits
0 | 18480 | 0 | 18480 | 0
1 | 7407 | 32407 | 25887 | 32407
2 | 7545 | 48011 | 33432 | 80418
3 | 7684 | 66682 | 41116 | 147100